## Master
PPC Production Planning Template | [18 empty] | ACTUALS — enter after shipment |  |  | NOTES
Month | Seq | Style | PO | ODR. Qty | Produce Till Date | Balance | Dely Date | Ex-Factory | Lines | Production/LINE | Days Req | Manual Start | Start Date | End Date | Projected Ex-Fac | Def | Fabric/Trims I/H Date | OTIF (Projected) | Actual Ex-Fac | Shipped Qty | OTIF (Actual) | Blue cells are inputs; grey cells are formulas.
M5 | 1 | 4300 | 7111632906 | 2678 | 2678 | 0 | 2026-08-05 | 2026-07-24 |  |  |  | Close | Close |  |  |  | - |  |  |  |  | Start Date: Manual Start wins. Otherwise the order starts 1 working day after the last planned end date of the same style above it.
M5 | 2 | 4300 | 7207749635 | 2950 | 0 | 2950 | 2026-08-05 | 2026-07-24 | 1 | 850 | 4 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-09-01 | -29 | 2026-08-11 | 0% |  |  |  | Type "Close" in Manual Start for an order that is finished or not to be scheduled.
M6 | 3 | 4300 | 7837962265 | 2580 | 0 | 2580 | 2026-08-28 | 2026-08-17 | 1 | 850 | 4 | 2026-08-28 | 2026-08-28 | 2026-09-02 | 2026-09-05 | -15 | 2026-08-17 | 0% |  |  |  | Planned Ex-Factory = Delivery date − 10 working days. Fabric/Trims in-house = Start − 10 working days.
M8 | 4 | 4300 | 7406530527 | 731 | 0 | 731 | 2026-11-06 | 2026-10-26 | 1 | 850 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-23 | 5 | 2026-10-07 | 100% |  |  |  | Projected Ex-Fac = End date + 3 working days. Def = working days of buffer between End date and Planned Ex-Factory (negative = late).
M9 | 5 | 4300 | 7601081513 | 1194 | 0 | 1194 | 2026-12-04 | 2026-11-23 | 1 | 850 | 2 |  | 2026-10-21 | 2026-10-22 | 2026-10-26 | 25 | 2026-10-08 | 100% |  |  |  | OTIF (Projected) = 1 if Projected Ex-Fac is at least 4 days before the delivery date. It is a forecast, not a result.
M5 | 1 | 4301 | 7040935107 | 4144 | 4144 | 0 | 2026-08-05 | 2026-07-24 |  |  |  | Close | Close |  |  |  | - |  |  |  |  | OTIF (Actual) = 1 only when the Actual Ex-Fac is at least 4 days before delivery AND Shipped Qty ≥ Order Qty.
M5 | 2 | 4301 | 7711945303 | 1190 | 1190 | 0 | 2026-08-14 | 2026-08-03 |  |  |  | Close | Close |  |  |  | - |  |  |  |  | Amber Lines / Production per line = the order still has a balance but no capacity assigned, so it is not scheduled.
M5 | 3 | 4301 | 7243553175 | 3693 | 3693 | 0 | 2026-08-05 | 2026-07-24 |  |  |  | Close | Close |  |  |  | - |  |  |  |  | Working days exclude Sundays and the dates listed on the Holidays sheet.
M5 | 4 | 4301 | 7906122198 | 803 | 586 | 217 | 2026-08-05 | 2026-07-24 |  |  |  | Close | Close |  |  |  | -
M5 | 5 | 4301 | 7972816177 | 3374 | 0 | 3374 | 2026-08-05 | 2026-07-24 | 1 | 850 | 4 | 2026-08-13 | 2026-08-13 | 2026-08-18 | 2026-08-21 | -22 | 2026-08-01 | 0%
M5 | 6 | 4301 | 7529999468 | 574 | 0 | 574 | 2026-08-14 | 2026-08-03 | 1 | 850 | 1 |  | 2026-08-19 | 2026-08-19 | 2026-08-22 | -15 | 2026-08-06 | 0%
M6 | 7 | 4301 | 7532230827 | 986 | 0 | 986 | 2026-09-11 | 2026-08-31 | 1 | 850 | 2 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-05 | -4 | 2026-08-19 | 100%
M6 | 8 | 4301 | 7114448904 | 659 | 659 | 0 | 2026-09-11 | 2026-08-31 | 1 | 850 | 0 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-03 | -2 | 2026-08-18 | 100%
M6 | 9 | 4301 | 7373337622 | 756 | 0 | 756 | 2026-09-11 | 2026-08-31 | 1 | 850 | 1 | 2026-08-29 | 2026-08-29 | 2026-08-29 | 2026-09-02 | 1 | 2026-08-17 | 100%
M6 | 10 | 4301 | 7665397029 | 2924 | 0 | 2924 | 2026-08-28 | 2026-08-17 | 1 | 850 | 4 | 2026-09-02 | 2026-09-02 | 2026-09-05 | 2026-09-09 | -17 | 2026-08-20 | 0%
M6 | 11 | 4301 | 7916958755 | 727 | 489 | 238 | 2026-08-28 | 2026-08-17 | 1 | 850 | 1 | 2026-09-05 | 2026-09-05 | 2026-09-05 | 2026-09-09 | -17 | 2026-08-24 | 0%
M6 | 12 | 4301 | 7207612821 | 1071 | 1071 | 0 | 2026-08-28 | 2026-08-17 | 1 | 850 | 0 |  | 2026-09-07 | 2026-09-07 | 2026-09-10 | -19 | 2026-08-25 | 0%
M6 | 13 | 4301 | 7883977575 | 2520 | 0 | 2520 | 2026-09-02 | 2026-08-20 | 1 | 850 | 3 |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | -19 | 2026-08-26 | 0%
M7 | 14 | 4301 | 7902771789 | 3804 | 0 | 3804 | 2026-09-30 | 2026-09-18 | 1 | 850 | 5 | 2026-09-12 | 2026-09-12 | 2026-09-17 | 2026-09-21 | 1 | 2026-09-01 | 100%
M7 | 15 | 4301 | 7861895544 | 2495 | 0 | 2495 | 2026-09-30 | 2026-09-18 | 1 | 850 | 3 |  | 2026-09-18 | 2026-09-21 | 2026-09-24 | -4 | 2026-09-07 | 100%
M7 | 16 | 4301 | 7589302773 | 926 | 0 | 926 | 2026-10-09 | 2026-09-26 | 1 | 850 | 2 |  | 2026-09-22 | 2026-09-23 | 2026-09-26 | 3 | 2026-09-10 | 100%
M8 | 17 | 4301 | 7435315852 | 544 | 0 | 544 | 2026-11-02 | 2026-10-21 | 1 | 850 | 1 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-09-26 | 22 | 2026-09-11 | 100%
M8 | 18 | 4301 | 7879518413 | 6668 | 0 | 6668 | 2026-10-23 | 2026-10-10 | 1 | 850 | 8 |  | 2026-09-24 | 2026-10-03 | 2026-10-07 | 6 | 2026-09-12 | 100%
M8 | 19 | 4301 | 7352175804 | 2231 | 0 | 2231 | 2026-10-23 | 2026-10-10 | 1 | 850 | 3 |  | 2026-10-05 | 2026-10-07 | 2026-10-10 | 3 | 2026-09-22 | 100%
M8 | 20 | 4301 | 7345360217 | 2796 | 0 | 2796 | 2026-10-23 | 2026-10-10 | 1 | 850 | 4 |  | 2026-10-08 | 2026-10-12 | 2026-10-15 | -3 | 2026-09-25 | 100%
M9 | 21 | 4301 | 7170179588 | 3145 | 0 | 3145 | 2026-11-22 | 2026-11-10 | 1 | 850 | 4 | 2026-10-12 | 2026-10-12 | 2026-10-15 | 2026-10-19 | 20 | 2026-09-29 | 100%
M9 | 22 | 4301 | 7881088803 | 1708 | 0 | 1708 | 2026-11-30 | 2026-11-18 | 1 | 850 | 3 |  | 2026-10-16 | 2026-10-19 | 2026-10-23 | 23 | 2026-10-05 | 100%
M5 | 1 | 6820 | 7232615519 | 64328 | 64328 | 0 | 2026-08-07 | 2026-07-27 |  |  |  | Close | Close |  |  |  | -
M5 | 2 | 6820 | 7121610466 | 63716 | 63716 | 0 | 2026-08-07 | 2026-07-27 |  |  |  | Close | Close |  |  |  | -
M6 | 3 | 6820 | 7161255896 | 51544 | 51544 | 0 | 2026-09-03 | 2026-08-21 |  |  |  | Close | Close |  |  |  | -
M6 | 4 | 6820 | 7330599164 | 51136 | 51136 | 0 | 2026-09-03 | 2026-08-21 |  |  |  | Close | Close |  |  |  | -
M7 | 5 | 6820 | 7447514654 | 59330 | 44573 | 14757 | 2026-10-07 | 2026-09-24 | 1 | 4250 | 4 | 2026-08-13 | 2026-08-13 | 2026-08-18 | 2026-08-21 | 31 | 2026-08-01 | 100%
M7 | 6 | 6820 | 7170997977 | 41922 | 0 | 41922 | 2026-10-07 | 2026-09-24 | 1 | 4250 | 10 | 2026-08-26 | 2026-08-26 | 2026-09-07 | 2026-09-10 | 15 | 2026-08-13 | 100%
M5 | 1 | RS26 | 7627387866 | 18062 | 18062 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 2 | RS26 | 7644351419 | 5453 | 5453 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 3 | RS26 | 7143748653 | 5958 | 5958 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 4 | RS26 | 7704849162 | 5504 | 5504 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 5 | RS26 | 7493971231 | 9524 | 9524 | 0 | 2026-08-17 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M5 | 6 | RS26 | 7533133898 | 4467 | 4467 | 0 | 2026-08-17 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M5 | 7 | RS26 | 7502906215 | 3961 | 3961 | 0 | 2026-08-17 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M5 | 8 | RS26 | 7294446425 | 4752 | 4752 | 0 | 2026-08-17 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M6 | 9 | RS26 | 7977288978 | 26533 | 13695 | 12838 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-17 | 2026-08-20 | 17 | 2026-08-01 | 100%
M6 | 10 | RS26 | 7702083978 | 18883 | 0 | 18883 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 4 | 2026-08-20 | 2026-08-20 | 2026-08-24 | 2026-08-27 | 11 | 2026-08-07 | 100%
M6 | 11 | RS26 | 7685354228 | 20366 | 0 | 20366 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 4 |  | 2026-08-25 | 2026-08-29 | 2026-09-02 | 7 | 2026-08-12 | 100%
M6 | 12 | RS26 | 7443774330 | 7892 | 0 | 7892 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 2 |  | 2026-08-31 | 2026-09-01 | 2026-09-04 | 5 | 2026-08-18 | 100%
M6 | 13 | RS26 | 7489342458 | 3413 | 0 | 3413 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 1 |  | 2026-09-02 | 2026-09-02 | 2026-09-05 | 4 | 2026-08-20 | 100%
M6 | 14 | RS26 | 7458868563 | 15874 | 2774 | 13100 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 3 |  | 2026-09-03 | 2026-09-05 | 2026-09-09 | 1 | 2026-08-21 | 100%
M7 | 15 | RS26 | 7962656881 | 7042 | 0 | 7042 | 2026-09-24 | 2026-09-12 | 2 | 2975 | 2 | 2026-09-12 | 2026-09-12 | 2026-09-14 | 2026-09-17 | -3 | 2026-09-01 | 100%
M7 | 16 | RS26 | 7355278063 | 5908 | 0 | 5908 | 2026-10-08 | 2026-09-25 | 2 | 2975 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-17 | 10 | 2026-09-02 | 100%
M7 | 17 | RS26 | 7231619297 | 7608 | 0 | 7608 | 2026-10-08 | 2026-09-25 | 2 | 2975 | 2 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-21 | 7 | 2026-09-04 | 100%
M7 | 18 | RS26 | 7673341236 | 19019 | 0 | 19019 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 4 | 2026-09-21 | 2026-09-21 | 2026-09-24 | 2026-09-28 | 8 | 2026-09-09 | 100%
M7 | 19 | RS26 | 7083400862 | 5869 | 0 | 5869 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 |  | 2026-09-25 | 2026-09-25 | 2026-09-29 | 7 | 2026-09-14 | 100%
M7 | 20 | RS26 | 7111923906 | 1228 | 0 | 1228 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 |  | 2026-09-26 | 2026-09-26 | 2026-09-30 | 6 | 2026-09-15 | 100%
M7 | 21 | RS26 | 7761246843 | 4203 | 0 | 4203 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 | 2026-09-26 | 2026-09-26 | 2026-09-26 | 2026-09-30 | 6 | 2026-09-15 | 100%
M7 | 22 | RS26 | 7320124062 | 2758 | 0 | 2758 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 |  | 2026-09-28 | 2026-09-28 | 2026-10-01 | 5 | 2026-09-16 | 100%
M5 | 1 | RS27 | 7038570281 | 2639 | 2639 | 0 | 2026-08-06 | 2026-07-25 |  |  |  | Close | Close |  |  |  | -
M5 | 2 | RS27 | 7393155065 | 4224 | 4224 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 3 | RS27 | 7507379931 | 1509 | 1509 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M6 | 4 | RS27 | 7183629647 | 5670 | 0 | 5670 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-10 | -2 | 2026-08-25 | 100%
M6 | 5 | RS27 | 7078111330 | 2750 | 0 | 2750 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-12 | -4 | 2026-08-27 | 100%
M6 | 6 | RS27 | 7509168631 | 6065 | 0 | 6065 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 2 |  | 2026-09-10 | 2026-09-11 | 2026-09-15 | -6 | 2026-08-29 | 0%
M6 | 7 | RS27 | 7650297685 | 2257 | 0 | 2257 | 2026-09-18 | 2026-09-07 | 2 | 2975 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-15 | -6 | 2026-08-31 | 0%
M7 | 8 | RS27 | 7626721491 | 3714 | 0 | 3714 | 2026-10-08 | 2026-09-25 | 2 | 2975 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-22 | 6 | 2026-09-07 | 100%
M7 | 9 | RS27 | 7728084997 | 404 | 0 | 404 | 2026-09-24 | 2026-09-12 | 2 | 2975 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-19 | -5 | 2026-09-04 | 100%
M7 | 10 | RS27 | 7854863949 | 1572 | 0 | 1572 | 2026-10-08 | 2026-09-25 | 2 | 2975 | 1 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 2026-09-23 | 5 | 2026-09-08 | 100%
M7 | 11 | RS27 | 7606870570 | 1768 | 0 | 1768 | 2026-10-08 | 2026-09-25 | 2 | 2975 | 1 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 2026-09-23 | 5 | 2026-09-08 | 100%
M7 | 12 | RS27 | 7039924412 | 1402 | 0 | 1402 | 2026-10-08 | 2026-09-25 | 2 | 2975 | 1 | 2026-09-19 | 2026-09-19 | 2026-09-19 | 2026-09-23 | 5 | 2026-09-08 | 100%
M7 | 13 | RS27 | 7849063489 | 2197 | 0 | 2197 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-10-03 | 4 | 2026-09-17 | 100%
M7 | 14 | RS27 | 7759903547 | 2614 | 0 | 2614 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-10-03 | 4 | 2026-09-17 | 100%
M7 | 15 | RS27 | 7084635043 | 1517 | 0 | 1517 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 |  | 2026-09-30 | 2026-09-30 | 2026-10-05 | 3 | 2026-09-18 | 100%
M7 | 16 | RS27 | 7009990468 | 1887 | 0 | 1887 | 2026-10-16 | 2026-10-05 | 2 | 2975 | 1 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-10-05 | 3 | 2026-09-18 | 100%
M5 | 1 | 4406 | 7448382145 | 125154 | 125154 | 0 | 2026-08-03 | 2026-07-22 |  |  |  | Close | Close |  |  |  | -
M6 | 1 | 4406P | 7248922049 | 70533 | 70533 | 0 | 2026-09-04 | 2026-08-22 |  |  |  | Close | Close |  |  |  | -
M6 | 2 | 4406P | 7290766807 | 70584 | 45140 | 25444 | 2026-09-04 | 2026-08-22 | 3 | 4250 | 2 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 6 | 2026-08-01 | 100%
M6 | 3 | 4406P | 7966735389 | 70482 | 0 | 70482 | 2026-09-04 | 2026-08-22 | 3 | 4250 | 6 | 2026-08-22 | 2026-08-22 | 2026-08-29 | 2026-09-02 | -6 | 2026-08-10 | 0%
M7 | 4 | 4406P | 7295058260 | 70278 | 0 | 70278 | 2026-09-25 | 2026-09-14 | 3 | 4250 | 6 | 2026-09-05 | 2026-09-05 | 2026-09-11 | 2026-09-15 | 2 | 2026-08-24 | 100%
M7 | 5 | 4406P | 7762431379 | 70482 | 0 | 70482 | 2026-09-25 | 2026-09-14 | 3 | 4250 | 6 | 2026-09-10 | 2026-09-10 | 2026-09-16 | 2026-09-19 | -4 | 2026-08-29 | 100%
M7 | 6 | 4406P | 7001886384 | 70176 | 0 | 70176 | 2026-09-25 | 2026-09-14 | 3 | 4250 | 6 | 2026-09-16 | 2026-09-16 | 2026-09-22 | 2026-09-25 | -9 | 2026-09-04 | 0%
M8 | 7 | 4406P | 7212591173 | 99348 | 0 | 99348 | 2026-10-23 | 2026-10-10 | 3 | 4250 | 8 | 2026-10-03 | 2026-10-03 | 2026-10-12 | 2026-10-15 | -3 | 2026-09-21 | 100%
M8 | 8 | 4406P | 7497573053 | 71196 | 0 | 71196 | 2026-11-13 | 2026-10-31 | 3 | 4250 | 6 |  | 2026-10-13 | 2026-10-19 | 2026-10-23 | 10 | 2026-09-30 | 100%
M7 | 1 | 4410P | 7492895374 | 57426 | 0 | 57426 | 2026-09-24 | 2026-09-12 | 3 | 4250 | 5 | 2026-08-31 | 2026-08-31 | 2026-09-04 | 2026-09-08 | 7 | 2026-08-18 | 100%
M7 | 2 | 4410P | 7430234996 | 48348 | 0 | 48348 | 2026-10-16 | 2026-10-05 | 3 | 4250 | 4 | 2026-09-22 | 2026-09-22 | 2026-09-25 | 2026-09-29 | 7 | 2026-09-10 | 100%
M8 | 3 | 4410P | 7254570238 | 51918 | 0 | 51918 | 2026-10-23 | 2026-10-10 | 3 | 4250 | 5 | 2026-09-28 | 2026-09-28 | 2026-10-03 | 2026-10-07 | 6 | 2026-09-16 | 100%
M5 | 1 | 6109 | 7885379839 | 28628 | 28628 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 2 | 6109 | 7236498977 | 28628 | 28628 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 3 | 6109 | 7047253536 | 45424 | 45424 | 0 | 2026-08-17 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M6 | 4 | 6109 | 7901407660 | 78540 | 78540 | 0 | 2026-08-22 | 2026-08-10 | 4 | 2550 | 0 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-18 | -5 | 2026-08-01 | 100%
M6 | 5 | 6109 | 7853440581 | 44846 | 6983 | 37863 | 2026-09-01 | 2026-08-19 | 4 | 2550 | 4 | 2026-08-17 | 2026-08-17 | 2026-08-20 | 2026-08-24 | -3 | 2026-08-04 | 100%
M6 | 6 | 6109 | 7211958562 | 44710 | 0 | 44710 | 2026-09-07 | 2026-08-25 | 4 | 2550 | 5 | 2026-08-25 | 2026-08-25 | 2026-08-31 | 2026-09-03 | -6 | 2026-08-12 | 100%
M6 | 7 | 6109 | 7453883288 | 49776 | 0 | 49776 | 2026-09-18 | 2026-09-07 | 4 | 2550 | 5 | 2026-09-02 | 2026-09-02 | 2026-09-07 | 2026-09-10 | -2 | 2026-08-20 | 100%
M6 | 8 | 6109 | 7345257873 | 44752 | 0 | 44752 | 2026-09-18 | 2026-09-07 | 4 | 2550 | 5 | 2026-09-10 | 2026-09-10 | 2026-09-15 | 2026-09-18 | -9 | 2026-08-29 | 0%
M7 | 9 | 6109 | 7080451197 | 62730 | 0 | 62730 | 2026-09-26 | 2026-09-15 | 4 | 2550 | 7 | 2026-09-15 | 2026-09-15 | 2026-09-22 | 2026-09-25 | -8 | 2026-09-03 | 0%
M7 | 10 | 6109 | 7358802573 | 76262 | 0 | 76262 | 2026-10-01 | 2026-09-19 | 4 | 2550 | 8 | 2026-09-21 | 2026-09-21 | 2026-09-29 | 2026-10-03 | -10 | 2026-09-09 | 0%
M7 | 11 | 6109 | 7799635923 | 57392 | 0 | 57392 | 2026-10-10 | 2026-09-28 | 4 | 2550 | 6 | 2026-10-01 | 2026-10-01 | 2026-10-08 | 2026-10-12 | -10 | 2026-09-19 | 0%
M5 | 1 | 4115 | 7239433937 | 60180 | 60180 | 0 | 2026-08-10 | 2026-07-29 |  |  |  | Close | Close |  |  |  | -
M6 | 2 | 4115 | 7018291935 | 29962 | 1479 | 28483 | 2026-09-14 | 2026-09-02 | 2 | 2125 | 7 | 2026-08-13 | 2026-08-13 | 2026-08-21 | 2026-08-25 | 9 | 2026-08-01 | 100%
M6 | 3 | 4115 | 7590742470 | 22066 | 0 | 22066 | 2026-09-14 | 2026-09-02 | 2 | 2125 | 6 | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-04 | 1 | 2026-08-12 | 100%
M7 | 4 | 4115 | 7621755697 | 26206 | 0 | 26206 | 2026-10-08 | 2026-09-25 | 2 | 2125 | 7 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-17 | 10 | 2026-08-25 | 100%
M7 | 5 | 4115 | 7663665933 | 10038 | 0 | 10038 | 2026-10-10 | 2026-09-28 | 2 | 2125 | 3 | 2026-09-19 | 2026-09-19 | 2026-09-22 | 2026-09-25 | 5 | 2026-09-08 | 100%
M7 | 6 | 4115 | 7525222549 | 16600 | 0 | 16600 | 2026-10-16 | 2026-10-05 | 2 | 2125 | 4 | 2026-09-24 | 2026-09-24 | 2026-09-28 | 2026-10-01 | 5 | 2026-09-12 | 100%
M5 | 1 | 4117 | 7281269433 | 46410 | 46410 | 0 | 2026-08-10 | 2026-07-29 |  |  |  | Close | Close |  |  |  | -
M5 | 2 | 4117 | 7399065641 | 46410 | 46410 | 0 | 2026-08-10 | 2026-07-29 |  |  |  | Close | Close |  |  |  | -
M5 | 3 | 4117 | 7160494479 | 23715 | 23715 | 0 | 2026-08-15 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M5 | 4 | 4117 | 7393933546 | 8126 | 8126 | 0 | 2026-08-20 | 2026-08-07 |  |  |  | Close | Close |  |  |  | -
M5 | 5 | 4117 | 7883578058 | 5550 | 5550 | 0 | 2026-08-17 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M6 | 6 | 4117 | 7910126782 | 22372 | 19574 | 2798 | 2026-09-07 | 2026-08-25 | 1 | 2125 | 2 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-19 | 8 | 2026-08-01 | 100%
M6 | 7 | 4117 | 7432281470 | 10370 | 6584 | 3786 | 2026-09-07 | 2026-08-25 | 1 | 2125 | 2 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-20 | 7 | 2026-08-03 | 100%
M6 | 8 | 4117 | 7715760122 | 64702 | 6791 | 57911 | 2026-09-14 | 2026-09-02 | 1 | 2125 | 28 | 2026-08-21 | 2026-08-21 | 2026-09-23 | 2026-09-26 | -20 | 2026-08-08 | 0%
M7 | 9 | 4117 | 7964904788 | 64770 | 0 | 64770 | 2026-09-28 | 2026-09-16 | 1 | 2125 | 31 | 2026-09-10 | 2026-09-10 | 2026-10-16 | 2026-10-21 | -27 | 2026-08-29 | 0%
M7 | 10 | 4117 | 7364057889 | 71077 | 0 | 71077 | 2026-10-15 | 2026-10-03 | 1 | 2125 | 34 | 2026-09-23 | 2026-09-23 | 2026-11-03 | 2026-11-06 | -27 | 2026-09-11 | 0%
M7 | 11 | 4117 | 7349215618 | 71111 | 0 | 71111 | 2026-10-15 | 2026-10-03 | 1 | 2125 | 34 | 2026-09-28 | 2026-09-28 | 2026-11-09 | 2026-11-12 | -31 | 2026-09-16 | 0%
M7 | 12 | 4117 | 7510045022 | 110313 | 0 | 110313 | 2026-10-16 | 2026-10-05 | 1 | 2125 | 52 | 2026-10-03 | 2026-10-03 | 2026-12-05 | 2026-12-09 | -51 | 2026-09-21 | 0%
M5 | 1 | 6108 | 7955138037 | 24310 | 24310 | 0 | 2026-08-05 | 2026-07-24 |  |  |  | Close | Close |  |  |  | -
M5 | 2 | 6108 | 7823249423 | 4012 | 4012 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 3 | 6108 | 7595169996 | 3774 | 3774 | 0 | 2026-08-15 | 2026-08-04 |  |  |  | Close | Close |  |  |  | -
M6 | 4 | 6108 | 7178507238 | 50320 | 50320 | 0 | 2026-09-14 | 2026-09-02 | 3 | 2550 | 0 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-18 | 15 | 2026-08-01 | 100%
M6 | 5 | 6108 | 7641277284 | 31450 | 14787 | 16663 | 2026-09-18 | 2026-09-07 | 3 | 2550 | 3 | 2026-08-13 | 2026-08-13 | 2026-08-17 | 2026-08-20 | 17 | 2026-08-01 | 100%
M6 | 6 | 6108 | 7252595077 | 48348 | 0 | 48348 | 2026-09-18 | 2026-09-07 | 3 | 2550 | 7 | 2026-08-21 | 2026-08-21 | 2026-08-29 | 2026-09-02 | 7 | 2026-08-08 | 100%
M6 | 1 | 6108 | 7488511959 | 71060 | 0 | 71060 | 2026-09-18 | 2026-09-07 | 3 | 2550 | 10 |  | 2026-08-31 | 2026-09-10 | 2026-09-14 | -5 | 2026-08-18 | 100%
M5 | 2 | 6135 | 7887760028 | 44064 | 44064 | 0 | 2026-08-05 | 2026-07-24 |  |  |  | Close | Close |  |  |  | -
M5 | 3 | 6135 | 7912888321 | 44166 | 44166 | 0 | 2026-08-05 | 2026-07-24 |  |  |  | Close | Close |  |  |  | -
M5 | 4 | 6135 | 7696645600 | 46818 | 46818 | 0 | 2026-08-20 | 2026-08-07 |  |  |  | Close | Close |  |  |  | -
M5 | 5 | 6135 | 7259723755 | 47226 | 47226 | 0 | 2026-08-20 | 2026-08-07 | 3 | 2550 | 0 | 2026-08-13 | 2026-08-13 | 2026-08-13 | 2026-08-18 | -7 | 2026-08-01 | 0%
M5 | 6 | 6135 | 7081702050 | 15376 | 15376 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M5 | 7 | 6135 | 7827988163 | 34612 | 34612 | 0 | 2026-08-13 | 2026-08-01 |  |  |  | Close | Close |  |  |  | -
M6 | 8 | 6135 | 7867355411 | 12444 | 0 | 12444 | 2026-09-14 | 2026-09-02 | 3 | 2550 | 2 |  | 2026-08-14 | 2026-08-17 | 2026-08-20 | 13 | 2026-08-03 | 100%
M6 | 9 | 6135 | 7143941962 | 49572 | 0 | 49572 | 2026-09-18 | 2026-09-07 | 3 | 2550 | 7 | 2026-08-20 | 2026-08-20 | 2026-08-27 | 2026-09-01 | 8 | 2026-08-07 | 100%
M7 | 10 | 6135 | 7448809399 | 17408 | 0 | 17408 | 2026-10-10 | 2026-09-28 | 3 | 2550 | 3 | 2026-09-02 | 2026-09-02 | 2026-09-04 | 2026-09-08 | 20 | 2026-08-20 | 100%
M6 | 1 | RS17 | 7184169015 | 71740 | 41423 | 30317 | 2026-08-29 | 2026-08-17 | 3 | 2125 | 5 | 2026-08-29 | 2026-08-29 | 2026-09-03 | 2026-09-07 | -16 | 2026-08-17 | 0%
M6 | 2 | RS17 | 7259213452 | 65195 | 0 | 65195 | 2026-09-14 | 2026-09-02 | 3 | 2125 | 11 | 2026-09-14 | 2026-09-14 | 2026-09-25 | 2026-09-29 | -22 | 2026-09-02 | 0%
M6 | 3 | RS17 | 7551311007 | 17289 | 0 | 17289 | 2026-09-14 | 2026-09-02 | 3 | 2125 | 3 | 2026-09-14 | 2026-09-14 | 2026-09-16 | 2026-09-19 | -14 | 2026-09-02 | 0%
M7 | 4 | RS17 | 7928146074 | 47056 | 0 | 47056 | 2026-10-16 | 2026-10-05 | 3 | 2125 | 8 | 2026-10-16 | 2026-10-16 | 2026-10-26 | 2026-10-29 | -19 | 2026-10-05 | 0%
M5 | 1 | 6137 | 7745344159 | 57936 | 57936 | 0 | 2026-08-15 | 2026-08-04 | 2 | 2550 | 0 | 2026-08-15 | 2026-08-15 | 2026-08-17 | 2026-08-20 | -12 | 2026-08-04 | 0%
M5 | 2 | 6137 | 7067945047 | 36448 | 36448 | 0 | 2026-08-15 | 2026-08-04 | 2 | 2550 | 0 | 2026-08-15 | 2026-08-15 | 2026-08-17 | 2026-08-20 | -12 | 2026-08-04 | 0%
M7 | 3 | 6137 | 7736519635 | 12512 | 0 | 12512 | 2026-10-10 | 2026-09-28 | 2 | 2550 | 3 | 2026-10-10 | 2026-10-10 | 2026-10-13 | 2026-10-16 | -14 | 2026-09-28 | 0%
M7 | 1 | 4110 | 7915846327 | 45067 | 0 | 45067 | 2026-09-24 | 2026-09-12 | 2 | 2550 | 9 | 2026-09-24 | 2026-09-24 | 2026-10-05 | 2026-10-08 | -20 | 2026-09-12 | 0%
M5 | 1 | 5501 | 7040000085 | 1742 | 1742 | 0 | 2026-08-20 | 2026-08-07 |  |  |  | 2026-08-20 | 2026-08-20 |  |  |  | 2026-08-07
M5 | 2 | 5501 | 7498532452 | 2231 | 0 | 2231 | 2026-08-20 | 2026-08-07 |  |  |  | 2026-08-20 | 2026-08-20 |  |  |  | 2026-08-07
M5 | 3 | 5501 | 7757901305 | 1764 | 1764 | 0 | 2026-08-20 | 2026-08-07 |  |  |  | 2026-08-20 | 2026-08-20 |  |  |  | 2026-08-07
M5 | 4 | 5501 | 7580454116 | 850 | 850 | 0 | 2026-08-20 | 2026-08-07 |  |  |  | 2026-08-20 | 2026-08-20 |  |  |  | 2026-08-07
M6 | 5 | 5501 | 7796826790 | 2338 | 567 | 1771 | 2026-09-17 | 2026-09-05 |  |  |  | 2026-09-17 | 2026-09-17 |  |  |  | 2026-09-05
M6 | 6 | 5501 | 7080992907 | 2954 | 0 | 2954 | 2026-09-17 | 2026-09-05 |  |  |  | 2026-09-17 | 2026-09-17 |  |  |  | 2026-09-05
M6 | 7 | 5501 | 7487079398 | 2359 | 2359 | 0 | 2026-09-17 | 2026-09-05 |  |  |  | 2026-09-17 | 2026-09-17 |  |  |  | 2026-09-05
M6 | 8 | 5501 | 7359668717 | 1148 | 565 | 583 | 2026-09-17 | 2026-09-05 |  |  |  | 2026-09-17 | 2026-09-17 |  |  |  | 2026-09-05
M5 |  | TH04 | 7387752475 | 1275 | 1275 | 0 | 2026-08-20 | 2026-08-07 | 4 | 850 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M5 |  | TH04 | 7033569591 | 892 | 892 | 0 | 2026-08-20 | 2026-08-07 | 4 | 850 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M6 |  | TH04 | 7533864431 | 1679 | 0 | 1679 | 2026-09-17 | 2026-09-05 | 4 | 850 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-21 | -12 | 2026-09-05 | 0%
M6 |  | TH04 | 7722747154 | 1169 | 0 | 1169 | 2026-09-17 | 2026-09-05 | 4 | 850 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-21 | -12 | 2026-09-05 | 0%
M7 |  | TH04 | 7909212191 | 722 | 0 | 722 | 2026-10-14 | 2026-10-01 | 4 | 850 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-17 | -12 | 2026-10-01 | 0%
M7 |  | TH04 | 7058983870 | 744 | 0 | 744 | 2026-10-14 | 2026-10-01 | 4 | 850 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-17 | -12 | 2026-10-01 | 0%
M5 |  | TH02 | 7888791922 | 8500 | 4646 | 3854 | 2026-08-20 | 2026-08-07 | 4 | 850 | 2 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-25 | -13 | 2026-08-07 | 0%
M5 |  | TH02 | 7373050972 | 5419 | 5313 | 106 | 2026-08-20 | 2026-08-07 | 4 | 850 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M6 |  | TH02 | 7793510346 | 11262 | 61 | 11201 | 2026-09-17 | 2026-09-05 | 4 | 850 | 4 | 2026-09-17 | 2026-09-17 | 2026-09-21 | 2026-09-24 | -15 | 2026-09-05 | 0%
M6 |  | TH02 | 7735945942 | 7182 | 0 | 7182 | 2026-09-17 | 2026-09-05 | 4 | 850 | 3 | 2026-09-17 | 2026-09-17 | 2026-09-19 | 2026-09-23 | -13 | 2026-09-05 | 0%
M7 |  | TH02 | 7673517982 | 3464 | 0 | 3464 | 2026-10-14 | 2026-10-01 | 4 | 850 | 2 | 2026-10-14 | 2026-10-14 | 2026-10-15 | 2026-10-19 | -13 | 2026-10-01 | 0%
M7 |  | TH02 | 7476533018 | 5584 | 0 | 5584 | 2026-10-14 | 2026-10-01 | 4 | 850 | 2 | 2026-10-14 | 2026-10-14 | 2026-10-15 | 2026-10-19 | -13 | 2026-10-01 | 0%
M7 |  | TH06 | 7147565668 | 15938 | 0 | 15938 | 2026-10-14 | 2026-10-01 | 4 | 850 | 5 | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-23 | -15 | 2026-10-01 | 0%
M7 |  | TH06 | 7663426096 | 12125 | 0 | 12125 | 2026-10-14 | 2026-10-01 | 4 | 850 | 4 | 2026-10-14 | 2026-10-14 | 2026-10-17 | 2026-10-22 | -14 | 2026-10-01 | 0%
M7 |  | TH07 | 7290518147 | 2805 | 0 | 2805 | 2026-10-14 | 2026-10-01 | 4 | 850 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-17 | -12 | 2026-10-01 | 0%
M7 |  | TH07 | 7012259170 | 956 | 0 | 956 | 2026-10-14 | 2026-10-01 | 4 | 850 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-17 | -12 | 2026-10-01 | 0%
M5 |  | TH01 | 7805283513 | 6672 | 6266 | 406 | 2026-08-20 | 2026-08-07 | 4 | 850 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M5 |  | TH01 | 7849081934 | 2975 | 2975 | 0 | 2026-08-20 | 2026-08-07 | 4 | 850 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M6 |  | TH01 | 7305497885 | 8861 | 0 | 8861 | 2026-09-17 | 2026-09-05 | 4 | 850 | 3 | 2026-09-17 | 2026-09-17 | 2026-09-19 | 2026-09-23 | -13 | 2026-09-05 | 0%
M6 |  | TH01 | 7176995317 | 3952 | 0 | 3952 | 2026-09-17 | 2026-09-05 | 4 | 850 | 2 | 2026-09-17 | 2026-09-17 | 2026-09-18 | 2026-09-22 | -13 | 2026-09-05 | 0%
M7 |  | TH01 | 7373845001 | 4378 | 0 | 4378 | 2026-10-14 | 2026-10-01 | 4 | 850 | 2 | 2026-10-14 | 2026-10-14 | 2026-10-15 | 2026-10-19 | -13 | 2026-10-01 | 0%
M7 |  | TH01 | 7301720304 | 2571 | 0 | 2571 | 2026-10-14 | 2026-10-01 | 4 | 850 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-17 | -12 | 2026-10-01 | 0%
M7 |  | TH05 | 7373434405 | 5716 | 0 | 5716 | 2026-10-14 | 2026-10-01 | 4 | 850 | 2 | 2026-10-14 | 2026-10-14 | 2026-10-15 | 2026-10-19 | -13 | 2026-10-01 | 0%
M7 |  | TH05 | 7758243055 | 8798 | 0 | 8798 | 2026-10-14 | 2026-10-01 | 4 | 850 | 3 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2026-10-21 | -14 | 2026-10-01 | 0%
M5 |  | 5520 | 7713625537 | 11071 | 11071 | 0 | 2026-08-20 | 2026-08-07 | 4 | 850 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M5 |  | 5520 | 7020412717 | 18360 | 0 | 18360 | 2026-08-20 | 2026-08-07 | 4 | 850 | 6 | 2026-08-20 | 2026-08-20 | 2026-08-26 | 2026-08-31 | -17 | 2026-08-07 | 0%
M5 |  | 5520 | 7551910352 | 5865 | 5865 | 0 | 2026-08-20 | 2026-08-07 | 4 | 850 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M5 |  | 5520 | 7530244571 | 4462 | 4462 | 0 | 2026-08-20 | 2026-08-07 | 4 | 850 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-24 | -12 | 2026-08-07 | 0%
M6 |  | 5520 | 7821026671 | 14726 | 0 | 14726 | 2026-09-17 | 2026-09-05 | 4 | 850 | 5 | 2026-09-17 | 2026-09-17 | 2026-09-22 | 2026-09-25 | -16 | 2026-09-05 | 0%
M6 |  | 5520 | 7603926568 | 24374 | 0 | 24374 | 2026-09-17 | 2026-09-05 | 4 | 850 | 8 | 2026-09-17 | 2026-09-17 | 2026-09-25 | 2026-09-29 | -19 | 2026-09-05 | 0%
M6 |  | 5520 | 7357771959 | 7756 | 2562 | 5194 | 2026-09-17 | 2026-09-05 | 4 | 850 | 2 | 2026-09-17 | 2026-09-17 | 2026-09-18 | 2026-09-22 | -13 | 2026-09-05 | 0%
M6 |  | 5520 | 7925096465 | 5950 | 0 | 5950 | 2026-09-17 | 2026-09-05 | 4 | 850 | 2 | 2026-09-17 | 2026-09-17 | 2026-09-18 | 2026-09-22 | -13 | 2026-09-05 | 0%
M4 |  | 7926 | 7364711569 | 987 | 0 | 987 | 2026-07-10 | 2026-06-29 |  |  |  | 2026-07-10 | 2026-07-10 |  |  |  | 2026-06-29
M5 |  | 7926 | 7919779616 | 4029 | 3123 | 906 | 2026-08-07 | 2026-07-27 |  |  |  | 2026-08-07 | 2026-08-07 |  |  |  | 2026-07-27
M5 |  | 7926 | 7681092268 | 4590 | 4590 | 0 | 2026-08-07 | 2026-07-27 |  |  |  | 2026-08-07 | 2026-08-07 |  |  |  | 2026-07-27
M5 |  | 7926 | 7405917663 | 7296 | 6260 | 1036 | 2026-08-05 | 2026-07-24 |  |  |  | 2026-08-05 | 2026-08-05 |  |  |  | 2026-07-24
M5 |  | 7926 | 7719305527 | 8548 | 6208 | 2340 | 2026-08-05 | 2026-07-24 |  |  |  | 2026-08-05 | 2026-08-05 |  |  |  | 2026-07-24
M5 |  | 7926 | 7785972195 | 1336 | 0 | 1336 | 2026-08-05 | 2026-07-24 |  |  |  | 2026-08-05 | 2026-08-05 |  |  |  | 2026-07-24
M6 |  | 7926 | 7884512003 | 3458 | 0 | 3458 | 2026-08-28 | 2026-08-17 |  |  |  | 2026-08-28 | 2026-08-28 |  |  |  | 2026-08-17
M6 |  | 7926 | 7198974414 | 1907 | 0 | 1907 | 2026-08-28 | 2026-08-17 |  |  |  | 2026-08-28 | 2026-08-28 |  |  |  | 2026-08-17
M6 |  | 7926 | 7842433484 | 5607 | 0 | 5607 | 2026-08-28 | 2026-08-17 |  |  |  | 2026-08-28 | 2026-08-28 |  |  |  | 2026-08-17
M7 |  | 7926 | 7142432145 | 6199 | 0 | 6199 | 2026-09-25 | 2026-09-14 |  |  |  | 2026-09-25 | 2026-09-25 |  |  |  | 2026-09-14
M7 |  | 7926 | 7833055688 | 5350 | 0 | 5350 | 2026-09-25 | 2026-09-14 |  |  |  | 2026-09-25 | 2026-09-25 |  |  |  | 2026-09-14
M7 |  | 7926 | 7955295810 | 1691 | 0 | 1691 | 2026-09-25 | 2026-09-14 |  |  |  | 2026-09-25 | 2026-09-25 |  |  |  | 2026-09-14
M8 |  | 7926 | 7988247306 | 4562 | 0 | 4562 | 2026-10-28 | 2026-10-15 |  |  |  | 2026-10-28 | 2026-10-28 |  |  |  | 2026-10-15
M8 |  | 7926 | 7289218292 | 6737 | 0 | 6737 | 2026-10-23 | 2026-10-10 |  |  |  | 2026-10-23 | 2026-10-23 |  |  |  | 2026-10-10
M8 |  | 7926 | 7044217852 | 4738 | 0 | 4738 | 2026-11-06 | 2026-10-26 |  |  |  | 2026-11-06 | 2026-11-06 |  |  |  | 2026-10-26
Formulas:
Ex-Factory = IF([Dely Date]="","",IFERROR(WORKDAY.INTL([Dely Date],-10,"0000001",Holidays!$A6:A55),"-"))
Start Date = IF(OR([Style]="",[PO]=""),"",IF([Manual Start]<>"",[Manual Start],IFERROR(WORKDAY.INTL(LOOKUP(2,1/((D2:[Style, row above]=[Style])*ISNUMBER(P2:[End Date, row above])),P2:[End Date, row above]),1,"0000001",Holidays!$A6:A55),"")))
End Date = IF(OR([Start Date]="",[Balance]="",[Lines]="",[Production/LINE]=""),"",IFERROR(WORKDAY.INTL([Start Date]-1,MAX(1,ROUNDUP([Balance]/([Lines]*[Production/LINE]),0)),"0000001",Holidays!$A6:A55),"-"))
Projected Ex-Fac = IF([End Date]="","",IFERROR(WORKDAY.INTL([End Date],3,"0000001",Holidays!$A6:A55),"-"))
Def = IF(OR([Ex-Factory]="",[End Date]=""),"",IFERROR(NETWORKDAYS.INTL([End Date]+1,[Ex-Factory],"0000001",Holidays!$A6:A55),"-"))
Fabric/Trims I/H Date = IF([Start Date]="","",IFERROR(WORKDAY.INTL([Start Date],-10,"0000001",Holidays!$A6:A55),"-"))

## Holidays
HOLIDAYS & WORKING CALENDAR
Calendar Year | 2026 |  | Legend | Working | Sunday | Holiday
Edit the yellow cells only: set the year in B2 and list holiday dates (and names) in A6:B55. Sundays are excluded automatically.
Holiday Register |  |  | Annual Working Calendar
Holiday Date | Holiday Name | Notes | Date | Month | Week | Day | Status | Counted?
2026-01-26 |  |  | 2026-01-01 | Jan | 1 | Thu | Working | Yes
2026-08-15 |  |  | 2026-01-02 | Jan | 1 | Fri | Working | Yes
2026-08-28 |  |  | 2026-01-03 | Jan | 1 | Sat | Working | Yes
2026-10-02 |  |  | 2026-01-04 | Jan | 1 | Sun | Sunday | No
2026-10-20 |  |  | 2026-01-05 | Jan | 2 | Mon | Working | Yes
2026-11-07 |  |  | 2026-01-06 | Jan | 2 | Tue | Working | Yes
2026-11-16 |  |  | 2026-01-07 | Jan | 2 | Wed | Working | Yes
|  |  | 2026-01-08 | Jan | 2 | Thu | Working | Yes
|  |  | 2026-01-09 | Jan | 2 | Fri | Working | Yes
|  |  | 2026-01-10 | Jan | 2 | Sat | Working | Yes
|  |  | 2026-01-11 | Jan | 2 | Sun | Sunday | No
|  |  | 2026-01-12 | Jan | 3 | Mon | Working | Yes
|  |  | 2026-01-13 | Jan | 3 | Tue | Working | Yes
|  |  | 2026-01-14 | Jan | 3 | Wed | Working | Yes
|  |  | 2026-01-15 | Jan | 3 | Thu | Working | Yes | 2026-08-30
|  |  | 2026-01-16 | Jan | 3 | Fri | Working | Yes | 2026-09-20
|  |  | 2026-01-17 | Jan | 3 | Sat | Working | Yes | 2026-10-18
|  |  | 2026-01-18 | Jan | 3 | Sun | Sunday | No
|  |  | 2026-01-19 | Jan | 4 | Mon | Working | Yes
|  |  | 2026-01-20 | Jan | 4 | Tue | Working | Yes
|  |  | 2026-01-21 | Jan | 4 | Wed | Working | Yes
|  |  | 2026-01-22 | Jan | 4 | Thu | Working | Yes
|  |  | 2026-01-23 | Jan | 4 | Fri | Working | Yes
|  |  | 2026-01-24 | Jan | 4 | Sat | Working | Yes
|  |  | 2026-01-25 | Jan | 4 | Sun | Sunday | No
|  |  | 2026-01-26 | Jan | 5 | Mon | Holiday | No
|  |  | 2026-01-27 | Jan | 5 | Tue | Working | Yes
|  |  | 2026-01-28 | Jan | 5 | Wed | Working | Yes
|  |  | 2026-01-29 | Jan | 5 | Thu | Working | Yes
|  |  | 2026-01-30 | Jan | 5 | Fri | Working | Yes
|  |  | 2026-01-31 | Jan | 5 | Sat | Working | Yes
|  |  | 2026-02-01 | Feb | 5 | Sun | Sunday | No
|  |  | 2026-02-02 | Feb | 6 | Mon | Working | Yes
|  |  | 2026-02-03 | Feb | 6 | Tue | Working | Yes
|  |  | 2026-02-04 | Feb | 6 | Wed | Working | Yes
|  |  | 2026-02-05 | Feb | 6 | Thu | Working | Yes
|  |  | 2026-02-06 | Feb | 6 | Fri | Working | Yes
|  |  | 2026-02-07 | Feb | 6 | Sat | Working | Yes
|  |  | 2026-02-08 | Feb | 6 | Sun | Sunday | No
|  |  | 2026-02-09 | Feb | 7 | Mon | Working | Yes
|  |  | 2026-02-10 | Feb | 7 | Tue | Working | Yes
|  |  | 2026-02-11 | Feb | 7 | Wed | Working | Yes
|  |  | 2026-02-12 | Feb | 7 | Thu | Working | Yes
|  |  | 2026-02-13 | Feb | 7 | Fri | Working | Yes
|  |  | 2026-02-14 | Feb | 7 | Sat | Working | Yes
|  |  | 2026-02-15 | Feb | 7 | Sun | Sunday | No
|  |  | 2026-02-16 | Feb | 8 | Mon | Working | Yes
|  |  | 2026-02-17 | Feb | 8 | Tue | Working | Yes
|  |  | 2026-02-18 | Feb | 8 | Wed | Working | Yes
|  |  | 2026-02-19 | Feb | 8 | Thu | Working | Yes
|  |  | 2026-02-20 | Feb | 8 | Fri | Working | Yes
|  |  | 2026-02-21 | Feb | 8 | Sat | Working | Yes
|  |  | 2026-02-22 | Feb | 8 | Sun | Sunday | No
|  |  | 2026-02-23 | Feb | 9 | Mon | Working | Yes
|  |  | 2026-02-24 | Feb | 9 | Tue | Working | Yes
|  |  | 2026-02-25 | Feb | 9 | Wed | Working | Yes
|  |  | 2026-02-26 | Feb | 9 | Thu | Working | Yes
|  |  | 2026-02-27 | Feb | 9 | Fri | Working | Yes
|  |  | 2026-02-28 | Feb | 9 | Sat | Working | Yes
|  |  | 2026-03-01 | Mar | 9 | Sun | Sunday | No
|  |  | 2026-03-02 | Mar | 10 | Mon | Working | Yes
|  |  | 2026-03-03 | Mar | 10 | Tue | Working | Yes
|  |  | 2026-03-04 | Mar | 10 | Wed | Working | Yes
|  |  | 2026-03-05 | Mar | 10 | Thu | Working | Yes
|  |  | 2026-03-06 | Mar | 10 | Fri | Working | Yes
|  |  | 2026-03-07 | Mar | 10 | Sat | Working | Yes
|  |  | 2026-03-08 | Mar | 10 | Sun | Sunday | No
|  |  | 2026-03-09 | Mar | 11 | Mon | Working | Yes
|  |  | 2026-03-10 | Mar | 11 | Tue | Working | Yes
|  |  | 2026-03-11 | Mar | 11 | Wed | Working | Yes
|  |  | 2026-03-12 | Mar | 11 | Thu | Working | Yes
|  |  | 2026-03-13 | Mar | 11 | Fri | Working | Yes
|  |  | 2026-03-14 | Mar | 11 | Sat | Working | Yes
|  |  | 2026-03-15 | Mar | 11 | Sun | Sunday | No
|  |  | 2026-03-16 | Mar | 12 | Mon | Working | Yes
|  |  | 2026-03-17 | Mar | 12 | Tue | Working | Yes
|  |  | 2026-03-18 | Mar | 12 | Wed | Working | Yes
|  |  | 2026-03-19 | Mar | 12 | Thu | Working | Yes
|  |  | 2026-03-20 | Mar | 12 | Fri | Working | Yes
|  |  | 2026-03-21 | Mar | 12 | Sat | Working | Yes
|  |  | 2026-03-22 | Mar | 12 | Sun | Sunday | No
|  |  | 2026-03-23 | Mar | 13 | Mon | Working | Yes
|  |  | 2026-03-24 | Mar | 13 | Tue | Working | Yes
|  |  | 2026-03-25 | Mar | 13 | Wed | Working | Yes
|  |  | 2026-03-26 | Mar | 13 | Thu | Working | Yes
|  |  | 2026-03-27 | Mar | 13 | Fri | Working | Yes
|  |  | 2026-03-28 | Mar | 13 | Sat | Working | Yes
|  |  | 2026-03-29 | Mar | 13 | Sun | Sunday | No
|  |  | 2026-03-30 | Mar | 14 | Mon | Working | Yes
|  |  | 2026-03-31 | Mar | 14 | Tue | Working | Yes
|  |  | 2026-04-01 | Apr | 14 | Wed | Working | Yes
|  |  | 2026-04-02 | Apr | 14 | Thu | Working | Yes
|  |  | 2026-04-03 | Apr | 14 | Fri | Working | Yes
|  |  | 2026-04-04 | Apr | 14 | Sat | Working | Yes
|  |  | 2026-04-05 | Apr | 14 | Sun | Sunday | No
|  |  | 2026-04-06 | Apr | 15 | Mon | Working | Yes
|  |  | 2026-04-07 | Apr | 15 | Tue | Working | Yes
|  |  | 2026-04-08 | Apr | 15 | Wed | Working | Yes
|  |  | 2026-04-09 | Apr | 15 | Thu | Working | Yes
|  |  | 2026-04-10 | Apr | 15 | Fri | Working | Yes
|  |  | 2026-04-11 | Apr | 15 | Sat | Working | Yes
|  |  | 2026-04-12 | Apr | 15 | Sun | Sunday | No
|  |  | 2026-04-13 | Apr | 16 | Mon | Working | Yes
|  |  | 2026-04-14 | Apr | 16 | Tue | Working | Yes
|  |  | 2026-04-15 | Apr | 16 | Wed | Working | Yes
|  |  | 2026-04-16 | Apr | 16 | Thu | Working | Yes
|  |  | 2026-04-17 | Apr | 16 | Fri | Working | Yes
|  |  | 2026-04-18 | Apr | 16 | Sat | Working | Yes
|  |  | 2026-04-19 | Apr | 16 | Sun | Sunday | No
|  |  | 2026-04-20 | Apr | 17 | Mon | Working | Yes
|  |  | 2026-04-21 | Apr | 17 | Tue | Working | Yes
|  |  | 2026-04-22 | Apr | 17 | Wed | Working | Yes
|  |  | 2026-04-23 | Apr | 17 | Thu | Working | Yes
|  |  | 2026-04-24 | Apr | 17 | Fri | Working | Yes
|  |  | 2026-04-25 | Apr | 17 | Sat | Working | Yes
|  |  | 2026-04-26 | Apr | 17 | Sun | Sunday | No
|  |  | 2026-04-27 | Apr | 18 | Mon | Working | Yes
|  |  | 2026-04-28 | Apr | 18 | Tue | Working | Yes
|  |  | 2026-04-29 | Apr | 18 | Wed | Working | Yes
|  |  | 2026-04-30 | Apr | 18 | Thu | Working | Yes
|  |  | 2026-05-01 | May | 18 | Fri | Working | Yes
|  |  | 2026-05-02 | May | 18 | Sat | Working | Yes
|  |  | 2026-05-03 | May | 18 | Sun | Sunday | No
|  |  | 2026-05-04 | May | 19 | Mon | Working | Yes
|  |  | 2026-05-05 | May | 19 | Tue | Working | Yes
|  |  | 2026-05-06 | May | 19 | Wed | Working | Yes
|  |  | 2026-05-07 | May | 19 | Thu | Working | Yes
|  |  | 2026-05-08 | May | 19 | Fri | Working | Yes
|  |  | 2026-05-09 | May | 19 | Sat | Working | Yes
|  |  | 2026-05-10 | May | 19 | Sun | Sunday | No
|  |  | 2026-05-11 | May | 20 | Mon | Working | Yes
|  |  | 2026-05-12 | May | 20 | Tue | Working | Yes
|  |  | 2026-05-13 | May | 20 | Wed | Working | Yes
|  |  | 2026-05-14 | May | 20 | Thu | Working | Yes
|  |  | 2026-05-15 | May | 20 | Fri | Working | Yes
|  |  | 2026-05-16 | May | 20 | Sat | Working | Yes
|  |  | 2026-05-17 | May | 20 | Sun | Sunday | No
|  |  | 2026-05-18 | May | 21 | Mon | Working | Yes
|  |  | 2026-05-19 | May | 21 | Tue | Working | Yes
|  |  | 2026-05-20 | May | 21 | Wed | Working | Yes
|  |  | 2026-05-21 | May | 21 | Thu | Working | Yes
|  |  | 2026-05-22 | May | 21 | Fri | Working | Yes
|  |  | 2026-05-23 | May | 21 | Sat | Working | Yes
|  |  | 2026-05-24 | May | 21 | Sun | Sunday | No
|  |  | 2026-05-25 | May | 22 | Mon | Working | Yes
|  |  | 2026-05-26 | May | 22 | Tue | Working | Yes
|  |  | 2026-05-27 | May | 22 | Wed | Working | Yes
|  |  | 2026-05-28 | May | 22 | Thu | Working | Yes
|  |  | 2026-05-29 | May | 22 | Fri | Working | Yes
|  |  | 2026-05-30 | May | 22 | Sat | Working | Yes
|  |  | 2026-05-31 | May | 22 | Sun | Sunday | No
|  |  | 2026-06-01 | Jun | 23 | Mon | Working | Yes
|  |  | 2026-06-02 | Jun | 23 | Tue | Working | Yes
|  |  | 2026-06-03 | Jun | 23 | Wed | Working | Yes
|  |  | 2026-06-04 | Jun | 23 | Thu | Working | Yes
|  |  | 2026-06-05 | Jun | 23 | Fri | Working | Yes
|  |  | 2026-06-06 | Jun | 23 | Sat | Working | Yes
|  |  | 2026-06-07 | Jun | 23 | Sun | Sunday | No
|  |  | 2026-06-08 | Jun | 24 | Mon | Working | Yes
|  |  | 2026-06-09 | Jun | 24 | Tue | Working | Yes
|  |  | 2026-06-10 | Jun | 24 | Wed | Working | Yes
|  |  | 2026-06-11 | Jun | 24 | Thu | Working | Yes
|  |  | 2026-06-12 | Jun | 24 | Fri | Working | Yes
|  |  | 2026-06-13 | Jun | 24 | Sat | Working | Yes
|  |  | 2026-06-14 | Jun | 24 | Sun | Sunday | No
|  |  | 2026-06-15 | Jun | 25 | Mon | Working | Yes
|  |  | 2026-06-16 | Jun | 25 | Tue | Working | Yes
|  |  | 2026-06-17 | Jun | 25 | Wed | Working | Yes
|  |  | 2026-06-18 | Jun | 25 | Thu | Working | Yes
|  |  | 2026-06-19 | Jun | 25 | Fri | Working | Yes
|  |  | 2026-06-20 | Jun | 25 | Sat | Working | Yes
|  |  | 2026-06-21 | Jun | 25 | Sun | Sunday | No
|  |  | 2026-06-22 | Jun | 26 | Mon | Working | Yes
|  |  | 2026-06-23 | Jun | 26 | Tue | Working | Yes
|  |  | 2026-06-24 | Jun | 26 | Wed | Working | Yes
|  |  | 2026-06-25 | Jun | 26 | Thu | Working | Yes
|  |  | 2026-06-26 | Jun | 26 | Fri | Working | Yes
|  |  | 2026-06-27 | Jun | 26 | Sat | Working | Yes
|  |  | 2026-06-28 | Jun | 26 | Sun | Sunday | No
|  |  | 2026-06-29 | Jun | 27 | Mon | Working | Yes
|  |  | 2026-06-30 | Jun | 27 | Tue | Working | Yes
|  |  | 2026-07-01 | Jul | 27 | Wed | Working | Yes
|  |  | 2026-07-02 | Jul | 27 | Thu | Working | Yes
|  |  | 2026-07-03 | Jul | 27 | Fri | Working | Yes
|  |  | 2026-07-04 | Jul | 27 | Sat | Working | Yes
|  |  | 2026-07-05 | Jul | 27 | Sun | Sunday | No
|  |  | 2026-07-06 | Jul | 28 | Mon | Working | Yes
|  |  | 2026-07-07 | Jul | 28 | Tue | Working | Yes
|  |  | 2026-07-08 | Jul | 28 | Wed | Working | Yes
|  |  | 2026-07-09 | Jul | 28 | Thu | Working | Yes
|  |  | 2026-07-10 | Jul | 28 | Fri | Working | Yes
|  |  | 2026-07-11 | Jul | 28 | Sat | Working | Yes
|  |  | 2026-07-12 | Jul | 28 | Sun | Sunday | No
|  |  | 2026-07-13 | Jul | 29 | Mon | Working | Yes
|  |  | 2026-07-14 | Jul | 29 | Tue | Working | Yes
|  |  | 2026-07-15 | Jul | 29 | Wed | Working | Yes
|  |  | 2026-07-16 | Jul | 29 | Thu | Working | Yes
|  |  | 2026-07-17 | Jul | 29 | Fri | Working | Yes
|  |  | 2026-07-18 | Jul | 29 | Sat | Working | Yes
|  |  | 2026-07-19 | Jul | 29 | Sun | Sunday | No
|  |  | 2026-07-20 | Jul | 30 | Mon | Working | Yes
|  |  | 2026-07-21 | Jul | 30 | Tue | Working | Yes
|  |  | 2026-07-22 | Jul | 30 | Wed | Working | Yes
|  |  | 2026-07-23 | Jul | 30 | Thu | Working | Yes
|  |  | 2026-07-24 | Jul | 30 | Fri | Working | Yes
|  |  | 2026-07-25 | Jul | 30 | Sat | Working | Yes
|  |  | 2026-07-26 | Jul | 30 | Sun | Sunday | No
|  |  | 2026-07-27 | Jul | 31 | Mon | Working | Yes
|  |  | 2026-07-28 | Jul | 31 | Tue | Working | Yes
|  |  | 2026-07-29 | Jul | 31 | Wed | Working | Yes
|  |  | 2026-07-30 | Jul | 31 | Thu | Working | Yes
|  |  | 2026-07-31 | Jul | 31 | Fri | Working | Yes
|  |  | 2026-08-01 | Aug | 31 | Sat | Working | Yes
|  |  | 2026-08-02 | Aug | 31 | Sun | Sunday | No
|  |  | 2026-08-03 | Aug | 32 | Mon | Working | Yes
|  |  | 2026-08-04 | Aug | 32 | Tue | Working | Yes
|  |  | 2026-08-05 | Aug | 32 | Wed | Working | Yes
|  |  | 2026-08-06 | Aug | 32 | Thu | Working | Yes
|  |  | 2026-08-07 | Aug | 32 | Fri | Working | Yes
|  |  | 2026-08-08 | Aug | 32 | Sat | Working | Yes
|  |  | 2026-08-09 | Aug | 32 | Sun | Sunday | No
|  |  | 2026-08-10 | Aug | 33 | Mon | Working | Yes
|  |  | 2026-08-11 | Aug | 33 | Tue | Working | Yes
|  |  | 2026-08-12 | Aug | 33 | Wed | Working | Yes
|  |  | 2026-08-13 | Aug | 33 | Thu | Working | Yes
|  |  | 2026-08-14 | Aug | 33 | Fri | Working | Yes
|  |  | 2026-08-15 | Aug | 33 | Sat | Holiday | No
|  |  | 2026-08-16 | Aug | 33 | Sun | Sunday | No
|  |  | 2026-08-17 | Aug | 34 | Mon | Working | Yes
|  |  | 2026-08-18 | Aug | 34 | Tue | Working | Yes
|  |  | 2026-08-19 | Aug | 34 | Wed | Working | Yes
|  |  | 2026-08-20 | Aug | 34 | Thu | Working | Yes
|  |  | 2026-08-21 | Aug | 34 | Fri | Working | Yes
|  |  | 2026-08-22 | Aug | 34 | Sat | Working | Yes
|  |  | 2026-08-23 | Aug | 34 | Sun | Sunday | No
|  |  | 2026-08-24 | Aug | 35 | Mon | Working | Yes
|  |  | 2026-08-25 | Aug | 35 | Tue | Working | Yes
|  |  | 2026-08-26 | Aug | 35 | Wed | Working | Yes
|  |  | 2026-08-27 | Aug | 35 | Thu | Working | Yes
|  |  | 2026-08-28 | Aug | 35 | Fri | Holiday | No
|  |  | 2026-08-29 | Aug | 35 | Sat | Working | Yes
|  |  | 2026-08-30 | Aug | 35 | Sun | Sunday | No
|  |  | 2026-08-31 | Aug | 36 | Mon | Working | Yes
|  |  | 2026-09-01 | Sep | 36 | Tue | Working | Yes
|  |  | 2026-09-02 | Sep | 36 | Wed | Working | Yes
|  |  | 2026-09-03 | Sep | 36 | Thu | Working | Yes
|  |  | 2026-09-04 | Sep | 36 | Fri | Working | Yes
|  |  | 2026-09-05 | Sep | 36 | Sat | Working | Yes
|  |  | 2026-09-06 | Sep | 36 | Sun | Sunday | No
|  |  | 2026-09-07 | Sep | 37 | Mon | Working | Yes
|  |  | 2026-09-08 | Sep | 37 | Tue | Working | Yes
|  |  | 2026-09-09 | Sep | 37 | Wed | Working | Yes
|  |  | 2026-09-10 | Sep | 37 | Thu | Working | Yes
|  |  | 2026-09-11 | Sep | 37 | Fri | Working | Yes
|  |  | 2026-09-12 | Sep | 37 | Sat | Working | Yes
|  |  | 2026-09-13 | Sep | 37 | Sun | Sunday | No
|  |  | 2026-09-14 | Sep | 38 | Mon | Working | Yes
|  |  | 2026-09-15 | Sep | 38 | Tue | Working | Yes
|  |  | 2026-09-16 | Sep | 38 | Wed | Working | Yes
|  |  | 2026-09-17 | Sep | 38 | Thu | Working | Yes
|  |  | 2026-09-18 | Sep | 38 | Fri | Working | Yes
|  |  | 2026-09-19 | Sep | 38 | Sat | Working | Yes
|  |  | 2026-09-20 | Sep | 38 | Sun | Sunday | No
|  |  | 2026-09-21 | Sep | 39 | Mon | Working | Yes
|  |  | 2026-09-22 | Sep | 39 | Tue | Working | Yes
|  |  | 2026-09-23 | Sep | 39 | Wed | Working | Yes
|  |  | 2026-09-24 | Sep | 39 | Thu | Working | Yes
|  |  | 2026-09-25 | Sep | 39 | Fri | Working | Yes
|  |  | 2026-09-26 | Sep | 39 | Sat | Working | Yes
|  |  | 2026-09-27 | Sep | 39 | Sun | Sunday | No
|  |  | 2026-09-28 | Sep | 40 | Mon | Working | Yes
|  |  | 2026-09-29 | Sep | 40 | Tue | Working | Yes
|  |  | 2026-09-30 | Sep | 40 | Wed | Working | Yes
|  |  | 2026-10-01 | Oct | 40 | Thu | Working | Yes
|  |  | 2026-10-02 | Oct | 40 | Fri | Holiday | No
|  |  | 2026-10-03 | Oct | 40 | Sat | Working | Yes
|  |  | 2026-10-04 | Oct | 40 | Sun | Sunday | No
|  |  | 2026-10-05 | Oct | 41 | Mon | Working | Yes
|  |  | 2026-10-06 | Oct | 41 | Tue | Working | Yes
|  |  | 2026-10-07 | Oct | 41 | Wed | Working | Yes
|  |  | 2026-10-08 | Oct | 41 | Thu | Working | Yes
|  |  | 2026-10-09 | Oct | 41 | Fri | Working | Yes
|  |  | 2026-10-10 | Oct | 41 | Sat | Working | Yes
|  |  | 2026-10-11 | Oct | 41 | Sun | Sunday | No
|  |  | 2026-10-12 | Oct | 42 | Mon | Working | Yes
|  |  | 2026-10-13 | Oct | 42 | Tue | Working | Yes
|  |  | 2026-10-14 | Oct | 42 | Wed | Working | Yes
|  |  | 2026-10-15 | Oct | 42 | Thu | Working | Yes
|  |  | 2026-10-16 | Oct | 42 | Fri | Working | Yes
|  |  | 2026-10-17 | Oct | 42 | Sat | Working | Yes
|  |  | 2026-10-18 | Oct | 42 | Sun | Sunday | No
|  |  | 2026-10-19 | Oct | 43 | Mon | Working | Yes
|  |  | 2026-10-20 | Oct | 43 | Tue | Holiday | No
|  |  | 2026-10-21 | Oct | 43 | Wed | Working | Yes
|  |  | 2026-10-22 | Oct | 43 | Thu | Working | Yes
|  |  | 2026-10-23 | Oct | 43 | Fri | Working | Yes
|  |  | 2026-10-24 | Oct | 43 | Sat | Working | Yes
|  |  | 2026-10-25 | Oct | 43 | Sun | Sunday | No
|  |  | 2026-10-26 | Oct | 44 | Mon | Working | Yes
|  |  | 2026-10-27 | Oct | 44 | Tue | Working | Yes
|  |  | 2026-10-28 | Oct | 44 | Wed | Working | Yes
|  |  | 2026-10-29 | Oct | 44 | Thu | Working | Yes
|  |  | 2026-10-30 | Oct | 44 | Fri | Working | Yes
|  |  | 2026-10-31 | Oct | 44 | Sat | Working | Yes
|  |  | 2026-11-01 | Nov | 44 | Sun | Sunday | No
|  |  | 2026-11-02 | Nov | 45 | Mon | Working | Yes
|  |  | 2026-11-03 | Nov | 45 | Tue | Working | Yes
|  |  | 2026-11-04 | Nov | 45 | Wed | Working | Yes
|  |  | 2026-11-05 | Nov | 45 | Thu | Working | Yes
|  |  | 2026-11-06 | Nov | 45 | Fri | Working | Yes
|  |  | 2026-11-07 | Nov | 45 | Sat | Holiday | No
|  |  | 2026-11-08 | Nov | 45 | Sun | Sunday | No
|  |  | 2026-11-09 | Nov | 46 | Mon | Working | Yes
|  |  | 2026-11-10 | Nov | 46 | Tue | Working | Yes
|  |  | 2026-11-11 | Nov | 46 | Wed | Working | Yes
|  |  | 2026-11-12 | Nov | 46 | Thu | Working | Yes
|  |  | 2026-11-13 | Nov | 46 | Fri | Working | Yes
|  |  | 2026-11-14 | Nov | 46 | Sat | Working | Yes
|  |  | 2026-11-15 | Nov | 46 | Sun | Sunday | No
|  |  | 2026-11-16 | Nov | 47 | Mon | Holiday | No
|  |  | 2026-11-17 | Nov | 47 | Tue | Working | Yes
|  |  | 2026-11-18 | Nov | 47 | Wed | Working | Yes
|  |  | 2026-11-19 | Nov | 47 | Thu | Working | Yes
|  |  | 2026-11-20 | Nov | 47 | Fri | Working | Yes
|  |  | 2026-11-21 | Nov | 47 | Sat | Working | Yes
|  |  | 2026-11-22 | Nov | 47 | Sun | Sunday | No
|  |  | 2026-11-23 | Nov | 48 | Mon | Working | Yes
|  |  | 2026-11-24 | Nov | 48 | Tue | Working | Yes
|  |  | 2026-11-25 | Nov | 48 | Wed | Working | Yes
|  |  | 2026-11-26 | Nov | 48 | Thu | Working | Yes
|  |  | 2026-11-27 | Nov | 48 | Fri | Working | Yes
|  |  | 2026-11-28 | Nov | 48 | Sat | Working | Yes
|  |  | 2026-11-29 | Nov | 48 | Sun | Sunday | No
|  |  | 2026-11-30 | Nov | 49 | Mon | Working | Yes
|  |  | 2026-12-01 | Dec | 49 | Tue | Working | Yes
|  |  | 2026-12-02 | Dec | 49 | Wed | Working | Yes
|  |  | 2026-12-03 | Dec | 49 | Thu | Working | Yes
|  |  | 2026-12-04 | Dec | 49 | Fri | Working | Yes
|  |  | 2026-12-05 | Dec | 49 | Sat | Working | Yes
|  |  | 2026-12-06 | Dec | 49 | Sun | Sunday | No
|  |  | 2026-12-07 | Dec | 50 | Mon | Working | Yes
|  |  | 2026-12-08 | Dec | 50 | Tue | Working | Yes
|  |  | 2026-12-09 | Dec | 50 | Wed | Working | Yes
|  |  | 2026-12-10 | Dec | 50 | Thu | Working | Yes
|  |  | 2026-12-11 | Dec | 50 | Fri | Working | Yes
|  |  | 2026-12-12 | Dec | 50 | Sat | Working | Yes
|  |  | 2026-12-13 | Dec | 50 | Sun | Sunday | No
|  |  | 2026-12-14 | Dec | 51 | Mon | Working | Yes
|  |  | 2026-12-15 | Dec | 51 | Tue | Working | Yes
|  |  | 2026-12-16 | Dec | 51 | Wed | Working | Yes
|  |  | 2026-12-17 | Dec | 51 | Thu | Working | Yes
|  |  | 2026-12-18 | Dec | 51 | Fri | Working | Yes
|  |  | 2026-12-19 | Dec | 51 | Sat | Working | Yes
|  |  | 2026-12-20 | Dec | 51 | Sun | Sunday | No
|  |  | 2026-12-21 | Dec | 52 | Mon | Working | Yes
|  |  | 2026-12-22 | Dec | 52 | Tue | Working | Yes
|  |  | 2026-12-23 | Dec | 52 | Wed | Working | Yes
|  |  | 2026-12-24 | Dec | 52 | Thu | Working | Yes
|  |  | 2026-12-25 | Dec | 52 | Fri | Working | Yes
|  |  | 2026-12-26 | Dec | 52 | Sat | Working | Yes
|  |  | 2026-12-27 | Dec | 52 | Sun | Sunday | No
|  |  | 2026-12-28 | Dec | 53 | Mon | Working | Yes
|  |  | 2026-12-29 | Dec | 53 | Tue | Working | Yes
|  |  | 2026-12-30 | Dec | 53 | Wed | Working | Yes
|  |  | 2026-12-31 | Dec | 53 | Thu | Working | Yes
Formulas:
Legend = IF([Legend, row above]="","",IF([Legend, row above]<DATE(B2+1,1,1)-1,[Legend, row above]+1,""))
Sunday = IF([Legend]="","",WEEKNUM([Legend],2))